## Capsule Low Acuity
Capsule Technologie Smartlinx ChartXpress

## Capsule High Acuity Site Status
High Acuity (Vitals Stream)
· Region/Sites server version and timeline for upgrade from Datacaptor to SmartLinx MDIS – Test server and one Production server are imaged, performing compatibility testing with Neuron 1’s in preparation for first site rollout.
· Planned projects - current and upcoming
· Known issues and status updates
SWOH
MHF – | Datacaptor 5.0; Windows Server 2003 -> SmartLinx (TBD)
MHA – | Datacaptor 6.8; Windows Server 2003 -> SmartLinx (TBD)
New Tower Neuron/Device moves and additions
MHC – | Datacaptor 6.8; Windows Server 2003 -> SmartLinx (TBD)
MOMC: Philips central station integration; schedule TBD
TJH - | Datacaptor 6.8; Windows Server 2003 -> SmartLinx (TBD)
New Tower Neuron/Device moves and additions
PACU move 150400-11353: scheduled for 4/2-3/16
Test revised DDI for TJH GE R860 ventilators
West - | Datacaptor 6.8; Windows Server 2008 -> SmartLinx (TBD)
Queen City ED move: coordinating with ASAP Team
MWM - | Datacaptor 6.8; Windows Server 2008 -> SmartLinx (TBD)
CMHP
SRMC - | Datacaptor 6.8; Windows Server 2003 -> SmartLinx (TBD)
CMHP CDU move to 1 North: date TBD; Kickoff 3/4/16
MMH - | Datacaptor 6.8; Windows Server 2003 -> SmartLinx (TBD)
HMHP
SEHC - | Datacaptor 6.8; Windows Server 2003 -> SmartLinx (TBD)
SEB - | Datacaptor 6.8; Windows Server 2003 -> SmartLinx (TBD)
SJHC - | Datacaptor 6.8; Windows Server 2003 -> SmartLinx (TBD)
WCOH
STR - | Datacaptor 6.8; Windows Server 2003 -> SmartLinx (TBD)
Cheetah NICOM (Non-invasive cardiac output monitoring)
MHPN/NDIV
STA - | Datacaptor 6.8; Windows Server 2008 -> SmartLinx (TBD)
STC – | Datacaptor 6.8; Windows Server 2008 -> SmartLinx (TBD)
STV - | Datacaptor 6.8; Windows Server 2003 -> SmartLinx (TBD)
MDH - | Datacaptor 6.8; Windows Server 2008 -> SmartLinx (TBD)
MTH - | Datacaptor 6.8; Windows Server 2003 -> SmartLinx upgade is SmartLinxated for the week of 4/18/16
MWH - | Datacaptor 6.8; Windows Server 2003 -> SmartLinx (TBD)
Optime for Northern Region – assess interface and Capsule server needs
KYIN
MHL - | Datacaptor 6.8; Windows Server 2008 -> SmartLinx (TBD)
SUMMA HEALTH
Akron City – TBD
Barberton (150280-16358) – SmartiInx HA interface to CarePATH
Philips OBTV interface to CarePATH
Go-live May 2016
CHPO
Scoping requirements

## Neuron Usage Guidelines
Neuron Usage Guidelines
A best practice of the CarePATH MDI Team is to periodically check the status of Capsule devices, particularly Neurons, to ensure that they are in good working order. At times we will notice that our monitoring console is displaying a “Not Connect” indicator. This tells us that either the unit is powered off, or there is some other issue which is preventing it from communicating with the Capsule middleware server. Typically, Biomed will assist us in determining the cause and we will jointly take action to restore it to service.
On other occasions we will discover that a large number of Neurons in a particular location are offline. This may indicate that they are not being actively utilized by the clinical staff. In this event, we will contact the hospital to assess the issue. If there are technical difficulties with Capsule hardware or software, we will work with the staff and Biomed to resolve. On the other hand, our assessment may determine that the staff is not using the equipment for other reasons. In this event the CarePATH MDI team will assist in reorientation or retraining as necessary. If in the end the Capsule solution is determined to be incompatible with a given department’s workflow, we will request that the hardware be reallocated for use by other sites or be transferred to our Neuron spares inventory.